## Human-readable
ID | Snapshot | Created | Status | Priority | Title | Assignee | Comment | Comment Reporter | Comment Date | Deadline | Reporter | Watchers | Tags | Stamp Abbreviation | Stamp Category | GUID | Closed Date | Procore Link | Level | Grid Location | Room | Space | Area | Zone | Stamp Title | Created from | Camera Position (m) | Camera Position (ft) | Coordinates (m) | Coordinates (ft) | Type | Status Category | RFI status | Linked RFI | Alignment | Coordinate on alignment | Anchor model name | Anchor model ID | Anchoring status | Fallback coordinates (m) | Fallback coordinates (ft)
42 | Snapshot | 2026-03-02 15:52 | In progress | Major | A040_Floor planning | admin rhyba-engineering.com |  |  |  | 2026-03-05 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | A040 | 01_Architecture | e04e32c8-3e71-4be3-a79b-0d3bb0cc2e50 |  |  | E03 |  |  | R301 |  | R301 | A040_Floor planning | THREE_D | (49.45; -128.88; 24.13) | (162.24; -422.85; 79.18) | (40.45; -128.98; 19.29) | (132.70; -423.15; 63.30) | A040_Floor planning | Tracking |  |  |  |  | 1321_02_3DM_PP1_Q_L01_PIP_XXX.dwg | 16321057641001081 | Active | (40.45; -128.98; 19.29) | (132.70; -423.15; 63.30)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-08 15:52
[7 empty] | make the floor out of chocolate | admin rhyba-engineering.com | 2026-04-08 15:54
43 | Snapshot | 2026-03-06 07:40 | In progress | Minor | A060_Support Planning | admin rhyba-engineering.com |  |  |  | 2026-03-07 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | A060 | 01_Architecture | d24a6d6a-187d-4c2e-82da-1e2e7c0389a0 |  |  | E03 |  |  | R300 |  | R300 | A060_Support Planning | THREE_D | (33.66; -93.71; 22.48) | (110.43; -307.45; 73.75) | (41.37; -95.56; 19.29) | (135.72; -313.53; 63.30) | A060_Support Planning | Tracking |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (41.37; -95.56; 19.29) | (135.72; -313.53; 63.30)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 07:40
44 | Snapshot | 2026-03-07 07:51 | Open | None | S020_Equipment | admin rhyba-engineering.com |  |  |  | 2026-03-10 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | S020 | 04_Sanitary | 6dda635e-8e13-4ff8-bd92-2edfbcf03f14 |  |  | E03 |  |  | R300 |  | R300 | S020_Equipment | THREE_D | (42.29; -98.52; 22.20) | (138.75; -323.24; 72.82) | (47.82; -95.64; 19.29) | (156.90; -313.77; 63.30) | S020_Equipment | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (47.82; -95.64; 19.29) | (156.90; -313.77; 63.30)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 07:51
45 | Snapshot | 2026-03-08 07:54 | Open | Major | P020_Equipment | admin rhyba-engineering.com |  |  |  | 2026-03-08 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | P020 | 05_Process Engineering | 786d6e4d-00b3-47c6-aabb-c917a0a79359 |  |  | E02 |  |  | R200 |  | R200 | P020_Equipment | THREE_D | (46.04; -95.75; 17.09) | (151.04; -314.15; 56.08) | (46.67; -93.95; 16.77) | (153.11; -308.24; 55.04) | P020_Equipment | To do |  |  |  |  | MASTER-REF-TRP-TP16-3DM-PIP_AVEVA.nwd | 5115858035720958311 | Active | (46.67; -93.95; 16.77) | (153.11; -308.24; 55.04)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 07:54
46 | Snapshot | 2026-03-09 07:55 | Open | None | A070_Openings and Penetration | admin rhyba-engineering.com |  |  |  | 2026-03-12 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | A070 | 01_Architecture | e91efd81-c7c0-4593-ad31-58d06f0a9dbe |  |  | E02 |  |  | R201 |  | R201 | A070_Openings and Penetration | THREE_D | (47.31; -129.41; 18.03) | (155.23; -424.57; 59.16) | (50.30; -130.72; 18.51) | (165.03; -428.87; 60.72) | A070_Openings and Penetration | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (50.30; -130.72; 18.51) | (165.03; -428.87; 60.72)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 07:55
47 | Snapshot | 2026-03-09 07:56 | In progress | Trivial | E020_Equipment | admin rhyba-engineering.com |  |  |  | 2026-03-12 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | E020 | 02_Electrical | 390deabe-2227-463d-8647-018922c0cd83 |  |  | E02 |  |  | R200 |  | R200 | E020_Equipment | THREE_D | (24.67; -99.55; 16.75) | (80.95; -326.61; 54.96) | (18.55; -93.09; 15.18) | (60.86; -305.41; 49.79) | E020_Equipment | Tracking |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (18.55; -93.09; 15.18) | (60.86; -305.41; 49.79)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 07:56
48 | Snapshot | 2026-03-10 07:56 | In progress | None | E070_Openings and Penetration | admin rhyba-engineering.com |  |  |  | 2026-03-15 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | E070 | 02_Electrical | dc483d00-933d-48bf-9fc3-093378d8ea84 |  |  | E02 |  |  | R200 |  | R200 | E070_Openings and Penetration | THREE_D | (24.67; -99.55; 16.75) | (80.95; -326.61; 54.96) | (21.99; -88.94; 15.08) | (72.14; -291.80; 49.46) | E070_Openings and Penetration | Tracking |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (21.99; -88.94; 15.08) | (72.14; -291.80; 49.46)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 07:56
49 | Snapshot | 2026-03-10 07:58 | Solved | Major | H010_PFD | admin rhyba-engineering.com |  |  |  | 2026-03-15 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | H010 | 03_HVAC | e63853cd-ef08-4cc0-8075-f395a24583c5 |  |  | E02 |  |  | R200 |  | R200 | H010_PFD | THREE_D | (24.67; -99.55; 16.75) | (80.95; -326.61; 54.96) | (23.88; -93.15; 18.51) | (78.33; -305.60; 60.72) | H010_PFD | Tracking |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (23.88; -93.15; 18.51) | (78.33; -305.60; 60.72)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 07:58
50 | Snapshot | 2026-03-10 08:00 | Open | None | H060_Support Planning | admin rhyba-engineering.com |  |  |  | 2026-03-18 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | H060 | 03_HVAC | d2cda2b3-6275-47ba-8f57-3d6192d24b58 |  |  | E02 |  |  | R200 |  | R200 | H060_Support Planning | THREE_D | (38.58; -95.04; 16.13) | (126.56; -311.81; 52.91) | (43.05; -88.94; 15.81) | (141.22; -291.80; 51.87) | H060_Support Planning | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (43.05; -88.94; 15.81) | (141.22; -291.80; 51.87)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:00
51 | Snapshot | 2026-03-15 08:01 | Open | None | Q030_Discipline Model Coordination | admin rhyba-engineering.com |  |  |  | Not set | admin rhyba-engineering.com | admin rhyba-engineering.com |  | Q030 | 06_BIM/3D-Coordination | 96f8eb04-c1cb-4884-823d-c6e61cdcf4d4 |  |  | E02 |  |  | R201 |  | R201 | Q030_Discipline Model Coordination | THREE_D | (30.07; -126.47; 14.73) | (98.66; -414.93; 48.33) | (39.07; -128.81; 12.93) | (128.20; -422.59; 42.43) | Q030_Discipline Model Coordination | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (39.07; -128.81; 12.93) | (128.20; -422.59; 42.43)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:01
52 | Snapshot | 2026-03-16 08:02 | Open | Blocker | Q070_Penetration Management | admin rhyba-engineering.com |  |  |  | 2026-03-20 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | Q070 | 06_BIM/3D-Coordination | 5efc7d0b-e8d5-445d-9642-dde2079d40f4 |  |  | E03 |  |  | R301 |  | R301 | Q070_Penetration Management | THREE_D | (30.07; -126.47; 21.12) | (98.66; -414.93; 69.28) | (37.15; -130.07; 19.29) | (121.90; -426.73; 63.30) | Q070_Penetration Management | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (37.15; -130.07; 19.29) | (121.90; -426.73; 63.30)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:02
53 | Snapshot | 2026-03-16 08:04 | Solved | None | S030_Arrangement | admin rhyba-engineering.com |  |  |  | Not set | admin rhyba-engineering.com | admin rhyba-engineering.com |  | S030 | 04_Sanitary | b8c51037-6945-48da-b6f3-aedc4bf9aa50 |  |  | E02 |  |  | R200 |  | R200 | S030_Arrangement | THREE_D | (23.58; -100.59; 17.15) | (77.37; -330.02; 56.28) | (21.93; -95.17; 16.72) | (71.96; -312.23; 54.85) | S030_Arrangement | Tracking |  |  |  |  | 1321_02_3DM_PP1_Q_L02_PIP_XXX.nwc | 8622159029130283572 | Active | (21.93; -95.17; 16.72) | (71.96; -312.23; 54.85)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:04
54 | Snapshot | 2026-03-23 08:10 | Open | None | Q050_Skid Coordination | admin rhyba-engineering.com |  |  |  | 2026-03-24 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | Q050 | 06_BIM/3D-Coordination | a4b91710-445a-4660-a6fb-1285a0801330 |  |  | E02 |  |  | R200 |  | R200 | Q050_Skid Coordination | THREE_D | (21.57; -96.84; 17.86) | (70.78; -317.73; 58.59) | (20.59; -94.45; 16.85) | (67.56; -309.88; 55.30) | Q050_Skid Coordination | To do |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (20.59; -94.45; 16.85) | (67.56; -309.88; 55.30)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:10
55 | Snapshot | 2026-04-07 08:11 | Open | None | P040_PID | admin rhyba-engineering.com |  |  |  | 2026-04-15 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | P040 | 05_Process Engineering | df3ecd2a-1ffa-4182-badb-b90dcc9c8a9e |  |  | E02 |  |  | R200 |  | R200 | P040_PID | THREE_D | (21.57; -96.84; 17.86) | (70.78; -317.73; 58.59) | (21.20; -93.69; 17.23) | (69.54; -307.39; 56.52) | P040_PID | To do |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (21.20; -93.69; 17.23) | (69.54; -307.39; 56.52)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:11
56 | Snapshot | 2026-04-08 08:12 | Open | None | P050_Assembly | admin rhyba-engineering.com |  |  |  | 2026-04-22 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | P050 | 05_Process Engineering | fd4c3ce4-cc8b-41f5-94ea-194816825378 |  |  | E01 |  |  | R100 |  | R100 | P050_Assembly | THREE_D | (45.38; -92.05; 10.50) | (148.88; -302.01; 34.45) | (48.12; -90.81; 11.18) | (157.87; -297.93; 36.68) | P050_Assembly | To do |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (48.12; -90.81; 11.18) | (157.87; -297.93; 36.68)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:12
57 | Snapshot | 2026-04-09 08:12 | In progress | None | Q070_Penetration Management | admin rhyba-engineering.com |  |  |  | 2026-04-14 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | Q070 | 06_BIM/3D-Coordination | 774e8b66-62a1-4ef2-b854-13ec0930a49e |  |  | E01 |  |  | R100 |  | R100 | Q070_Penetration Management | THREE_D | (53.10; -96.24; 11.72) | (174.22; -315.74; 38.46) | (53.15; -93.14; 12.15) | (174.38; -305.56; 39.85) | Q070_Penetration Management | Tracking |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (53.15; -93.14; 12.15) | (174.38; -305.56; 39.85)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:12
58 | Snapshot | 2026-04-09 08:13 | In progress | None | H020_Equipment | admin rhyba-engineering.com |  |  |  | 2026-04-29 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | H020 | 03_HVAC | 2762cc2a-9999-41b3-a74a-deb83c488e63 |  |  | E01 |  |  | R100 |  | R100 | H020_Equipment | THREE_D | (53.10; -96.24; 11.72) | (174.22; -315.74; 38.46) | (48.86; -92.18; 12.15) | (160.31; -302.43; 39.85) | H020_Equipment | Tracking |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (48.86; -92.18; 12.15) | (160.31; -302.43; 39.85)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:13
59 | Snapshot | 2026-04-09 08:13 | Open | None | P040_PID | admin rhyba-engineering.com |  |  |  | 2026-04-21 12:00 | admin rhyba-engineering.com | admin rhyba-engineering.com |  | P040 | 05_Process Engineering | d4478c86-a99f-4484-80db-d1c73a057843 |  |  | E01 |  |  | R100 |  | R100 | P040_PID | THREE_D | (53.10; -96.24; 11.72) | (174.22; -315.74; 38.46) | (51.24; -92.48; 11.34) | (168.10; -303.42; 37.20) | P040_PID | To do |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (51.24; -92.48; 11.34) | (168.10; -303.42; 37.20)
[7 empty] | Original Markup | admin rhyba-engineering.com | 2026-04-09 08:13

## Raw Data
GUID | ID | Snapshot | Created | Status | Priority | Title | Assignee | Reporter | Deadline | Watchers | Tags | Stamp Abbreviation | Stamp Category | Public | Last Updated | Last In-Progress | Last Solved | Last Closed | Last Comment | Number of Comments | Camera | Sheet | Clash GUID | Clash Name | Clash Test | Clash Group | Discipline | Category | Level | Source File | Grid Location | Distance | Element IDs | Selection | Authoring selection | Closed Date | Procore Link | Room | Space | Area | Zone | Stamp Title | Created from | Camera Position (m) | Camera Position (ft) | Coordinates (m) | Coordinates (ft) | Type | Status Category | RFI status | Linked RFI | Alignment | Coordinate on alignment | Anchor model name | Anchor model ID | Anchoring status | Fallback coordinates (m) | Fallback coordinates (ft)
e04e32c8-3e71-4be3-a79b-0d3bb0cc2e50 | 42 | Snapshot | 2026-03-02 15:52 | In progress | Major | A040_Floor planning | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-05 12:00 | admin rhyba-engineering.com |  | A040 | 01_Architecture | true | 2026-04-09 08:14 | 2026-04-09 08:14 |  |  | [4/8/2026 3:53:54 PM] admin rhyba-engineering.com (admin@rhyba-engineering.com): make the floor out of chocolate | 1 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.8241539,"y":-0.5528759,"z":-0.1228766},"forward_bind":{"x":0.8241539,"y":-0.5528759,"z":-0.1228766},"fov":50.25556,"position":{"x":-162.2364,"y":79.17756,"z":422.8459},"position_bind":{"x":-162.236404418945,"y":79.1775588989258,"z":422.845886230469},"target":{"x":-132.6954,"y":63.29843,"z":423.15},"target_bind":{"x":-132.695404052734,"y":63.2984275817871,"z":423.149963378906},"type":0,"up":{"x":0.5468315,"y":0.8332636,"z":-0.08152939},"up_bind":{"x":0.5468315,"y":0.8332636,"z":-0.08152939},"viewToWorldScale":9.995695} | [7 empty] | E03 |  |  |  |  | 16321057641001081:-1496831712240088786 | 470C |  |  |  | R301 |  | R301 | A040_Floor planning | THREE_D | (49.45; -128.88; 24.13) | (162.24; -422.85; 79.18) | (40.45; -128.98; 19.29) | (132.70; -423.15; 63.30) | A040_Floor planning | Tracking |  |  |  |  | 1321_02_3DM_PP1_Q_L01_PIP_XXX.dwg | 16321057641001081 | Active | (40.45; -128.98; 19.29) | (132.70; -423.15; 63.30)
d24a6d6a-187d-4c2e-82da-1e2e7c0389a0 | 43 | Snapshot | 2026-03-06 07:40 | In progress | Minor | A060_Support Planning | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-07 12:00 | admin rhyba-engineering.com |  | A060 | 01_Architecture | true | 2026-04-09 08:14 | 2026-04-09 08:14 |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":-0.7986372,"y":-0.2833248,"z":0.5309479},"forward_bind":{"x":-0.7986372,"y":-0.2833248,"z":0.5309479},"fov":50.25556,"position":{"x":-110.4303,"y":73.75305,"z":307.4456},"position_bind":{"x":-110.430267333984,"y":73.7530517578125,"z":307.445556640625},"target":{"x":-135.7244,"y":63.29843,"z":313.5318},"target_bind":{"x":-135.724411010742,"y":63.2984275817871,"z":313.531768798828},"type":0,"up":{"x":-0.2359417,"y":0.959024,"z":0.1568581},"up_bind":{"x":-0.2359417,"y":0.959024,"z":0.1568581},"viewToWorldScale":13.12348} | [7 empty] | E03 | [9 empty] | R300 |  | R300 | A060_Support Planning | THREE_D | (33.66; -93.71; 22.48) | (110.43; -307.45; 73.75) | (41.37; -95.56; 19.29) | (135.72; -313.53; 63.30) | A060_Support Planning | Tracking |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (41.37; -95.56; 19.29) | (135.72; -313.53; 63.30)
6dda635e-8e13-4ff8-bd92-2edfbcf03f14 | 44 | Snapshot | 2026-03-07 07:51 | Open | None | S020_Equipment | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-10 12:00 | admin rhyba-engineering.com |  | S020 | 04_Sanitary | true | 2026-04-09 07:51 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":-0.793716,"y":-0.2843094,"z":-0.5377575},"forward_bind":{"x":-0.793716,"y":-0.2843094,"z":-0.5377575},"fov":50.25556,"position":{"x":-138.7542,"y":72.82272,"z":323.2355},"position_bind":{"x":-138.754241943359,"y":72.8227157592773,"z":323.235473632813},"target":{"x":-156.8983,"y":63.29842,"z":313.7659},"target_bind":{"x":-156.898315429688,"y":63.2984237670898,"z":313.765930175781},"type":0,"up":{"x":-0.2353742,"y":0.9587326,"z":-0.1594704},"up_bind":{"x":-0.2353742,"y":0.9587326,"z":-0.1594704},"viewToWorldScale":6.907726} | [7 empty] | E03 | [9 empty] | R300 |  | R300 | S020_Equipment | THREE_D | (42.29; -98.52; 22.20) | (138.75; -323.24; 72.82) | (47.82; -95.64; 19.29) | (156.90; -313.77; 63.30) | S020_Equipment | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (47.82; -95.64; 19.29) | (156.90; -313.77; 63.30)
786d6e4d-00b3-47c6-aabb-c917a0a79359 | 45 | Snapshot | 2026-03-08 07:54 | Open | Major | P020_Equipment | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-08 12:00 | admin rhyba-engineering.com |  | P020 | 05_Process Engineering | true | 2026-04-09 07:54 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":-0.4731554,"y":-0.3124172,"z":-0.8237229},"forward_bind":{"x":-0.4731554,"y":-0.3124172,"z":-0.8237229},"fov":50.25556,"position":{"x":-151.0428,"y":56.08156,"z":314.1513},"position_bind":{"x":224.746810913086,"y":39.9697494506836,"z":37.1502685546875},"target":{"x":-153.111,"y":55.03513,"z":308.2392},"target_bind":{"x":222.678665161133,"y":38.9233245849609,"z":31.2381286621094},"type":0,"up":{"x":-0.1556111,"y":0.949945,"z":-0.2709054},"up_bind":{"x":-0.1556111,"y":0.949945,"z":-0.2709054},"viewToWorldScale":4.113012} | [7 empty] | E02 | [9 empty] | R200 |  | R200 | P020_Equipment | THREE_D | (46.04; -95.75; 17.09) | (151.04; -314.15; 56.08) | (46.67; -93.95; 16.77) | (153.11; -308.24; 55.04) | P020_Equipment | To do |  |  |  |  | MASTER-REF-TRP-TP16-3DM-PIP_AVEVA.nwd | 5115858035720958311 | Active | (46.67; -93.95; 16.77) | (153.11; -308.24; 55.04)
e91efd81-c7c0-4593-ad31-58d06f0a9dbe | 46 | Snapshot | 2026-03-09 07:55 | Open | None | A070_Openings and Penetration | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-12 12:00 | admin rhyba-engineering.com |  | A070 | 01_Architecture | true | 2026-04-09 07:55 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":-0.7520853,"y":0.002003022,"z":0.6590627},"forward_bind":{"x":-0.7520853,"y":0.002003022,"z":0.6590627},"fov":50.25556,"position":{"x":-155.2298,"y":59.15587,"z":424.5679},"position_bind":{"x":-155.229843139648,"y":59.1558723449707,"z":424.56787109375},"target":{"x":-165.0308,"y":60.71733,"z":428.8697},"target_bind":{"x":-165.03076171875,"y":60.7173271179199,"z":428.869720458984},"type":0,"up":{"x":0.001506446,"y":0.999998,"z":-0.00132012},"up_bind":{"x":0.001506446,"y":0.999998,"z":-0.00132012},"viewToWorldScale":12.20665} | [7 empty] | E02 | [9 empty] | R201 |  | R201 | A070_Openings and Penetration | THREE_D | (47.31; -129.41; 18.03) | (155.23; -424.57; 59.16) | (50.30; -130.72; 18.51) | (165.03; -428.87; 60.72) | A070_Openings and Penetration | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (50.30; -130.72; 18.51) | (165.03; -428.87; 60.72)
390deabe-2227-463d-8647-018922c0cd83 | 47 | Snapshot | 2026-03-09 07:56 | In progress | Trivial | E020_Equipment | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-12 12:00 | admin rhyba-engineering.com |  | E020 | 02_Electrical | true | 2026-04-09 08:14 | 2026-04-09 08:14 |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.3013371,"y":-0.06554841,"z":-0.951262},"forward_bind":{"x":0.3013371,"y":-0.06554841,"z":-0.951262},"fov":50.25556,"position":{"x":-80.95393,"y":54.96155,"z":326.6123},"position_bind":{"x":-80.9539337158203,"y":54.9615516662598,"z":326.612335205078},"target":{"x":-60.8647,"y":49.79099,"z":305.4069},"target_bind":{"x":-60.8647041320801,"y":49.7909927368164,"z":305.406890869141},"type":0,"up":{"x":0.01979474,"y":0.9978494,"z":-0.0624881},"up_bind":{"x":0.01979474,"y":0.9978494,"z":-0.0624881},"viewToWorldScale":12.44335} | [7 empty] | E02 | [9 empty] | R200 |  | R200 | E020_Equipment | THREE_D | (24.67; -99.55; 16.75) | (80.95; -326.61; 54.96) | (18.55; -93.09; 15.18) | (60.86; -305.41; 49.79) | E020_Equipment | Tracking |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (18.55; -93.09; 15.18) | (60.86; -305.41; 49.79)
dc483d00-933d-48bf-9fc3-093378d8ea84 | 48 | Snapshot | 2026-03-10 07:56 | In progress | None | E070_Openings and Penetration | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-15 12:00 | admin rhyba-engineering.com |  | E070 | 02_Electrical | true | 2026-04-09 08:14 | 2026-04-09 08:14 |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.3013371,"y":-0.06554841,"z":-0.951262},"forward_bind":{"x":0.3013371,"y":-0.06554841,"z":-0.951262},"fov":50.25556,"position":{"x":-80.95393,"y":54.96155,"z":326.6123},"position_bind":{"x":-80.9539337158203,"y":54.9615516662598,"z":326.612335205078},"target":{"x":-72.13509,"y":49.46028,"z":291.8017},"target_bind":{"x":-72.1350860595703,"y":49.460277557373,"z":291.801696777344},"type":0,"up":{"x":0.01979474,"y":0.9978494,"z":-0.0624881},"up_bind":{"x":0.01979474,"y":0.9978494,"z":-0.0624881},"viewToWorldScale":12.44335} | [7 empty] | E02 | [9 empty] | R200 |  | R200 | E070_Openings and Penetration | THREE_D | (24.67; -99.55; 16.75) | (80.95; -326.61; 54.96) | (21.99; -88.94; 15.08) | (72.14; -291.80; 49.46) | E070_Openings and Penetration | Tracking |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (21.99; -88.94; 15.08) | (72.14; -291.80; 49.46)
e63853cd-ef08-4cc0-8075-f395a24583c5 | 49 | Snapshot | 2026-03-10 07:58 | Solved | Major | H010_PFD | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-15 12:00 | admin rhyba-engineering.com |  | H010 | 03_HVAC | true | 2026-04-09 08:14 |  | 2026-04-09 08:14 |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.3013371,"y":-0.06554841,"z":-0.951262},"forward_bind":{"x":0.3013371,"y":-0.06554841,"z":-0.951262},"fov":50.25556,"position":{"x":-80.95393,"y":54.96155,"z":326.6123},"position_bind":{"x":-80.9539337158203,"y":54.9615516662598,"z":326.612335205078},"target":{"x":-78.33098,"y":60.71733,"z":305.5977},"target_bind":{"x":-78.3309783935547,"y":60.7173271179199,"z":305.59765625},"type":0,"up":{"x":0.01979474,"y":0.9978494,"z":-0.0624881},"up_bind":{"x":0.01979474,"y":0.9978494,"z":-0.0624881},"viewToWorldScale":12.44335} | [7 empty] | E02 | [9 empty] | R200 |  | R200 | H010_PFD | THREE_D | (24.67; -99.55; 16.75) | (80.95; -326.61; 54.96) | (23.88; -93.15; 18.51) | (78.33; -305.60; 60.72) | H010_PFD | Tracking |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (23.88; -93.15; 18.51) | (78.33; -305.60; 60.72)
d2cda2b3-6275-47ba-8f57-3d6192d24b58 | 50 | Snapshot | 2026-03-10 08:00 | Open | None | H060_Support Planning | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-18 12:00 | admin rhyba-engineering.com |  | H060 | 03_HVAC | true | 2026-04-09 08:00 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":-0.764246,"y":-0.07027614,"z":-0.6410844},"forward_bind":{"x":-0.764246,"y":-0.07027614,"z":-0.6410844},"fov":50.25556,"position":{"x":-126.5603,"y":52.9075,"z":311.8054},"position_bind":{"x":-126.560317993164,"y":52.9075012207031,"z":311.805358886719},"target":{"x":-141.2249,"y":51.87283,"z":291.8017},"target_bind":{"x":-141.224914550781,"y":51.8728256225586,"z":291.801696777344},"type":0,"up":{"x":-0.05384139,"y":0.9975276,"z":-0.0451646},"up_bind":{"x":-0.05384139,"y":0.9975276,"z":-0.0451646},"viewToWorldScale":10.76492} | [7 empty] | E02 | [9 empty] | R200 |  | R200 | H060_Support Planning | THREE_D | (38.58; -95.04; 16.13) | (126.56; -311.81; 52.91) | (43.05; -88.94; 15.81) | (141.22; -291.80; 51.87) | H060_Support Planning | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (43.05; -88.94; 15.81) | (141.22; -291.80; 51.87)
96f8eb04-c1cb-4884-823d-c6e61cdcf4d4 | 51 | Snapshot | 2026-03-15 08:01 | Open | None | Q030_Discipline Model Coordination | admin rhyba-engineering.com | admin rhyba-engineering.com | Not set | admin rhyba-engineering.com |  | Q030 | 06_BIM/3D-Coordination | true | 2026-04-09 08:01 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":-0.8618414,"y":0.05424137,"z":0.5042689},"forward_bind":{"x":-0.8618414,"y":0.05424137,"z":0.5042689},"fov":50.25556,"position":{"x":-98.65538,"y":48.3312,"z":414.9276},"position_bind":{"x":-98.6553802490234,"y":48.3311958312988,"z":414.927642822266},"target":{"x":-128.1958,"y":42.43229,"z":422.5948},"target_bind":{"x":-128.195770263672,"y":42.4322891235352,"z":422.594818115234},"type":0,"up":{"x":0.04681638,"y":0.9985278,"z":-0.02739257},"up_bind":{"x":0.04681638,"y":0.9985278,"z":-0.02739257},"viewToWorldScale":22.3261} | [7 empty] | E02 | [9 empty] | R201 |  | R201 | Q030_Discipline Model Coordination | THREE_D | (30.07; -126.47; 14.73) | (98.66; -414.93; 48.33) | (39.07; -128.81; 12.93) | (128.20; -422.59; 42.43) | Q030_Discipline Model Coordination | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (39.07; -128.81; 12.93) | (128.20; -422.59; 42.43)
5efc7d0b-e8d5-445d-9642-dde2079d40f4 | 52 | Snapshot | 2026-03-16 08:02 | Open | Blocker | Q070_Penetration Management | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-20 12:00 | admin rhyba-engineering.com |  | Q070 | 06_BIM/3D-Coordination | true | 2026-04-09 08:03 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":-0.8618414,"y":0.05424137,"z":0.5042689},"forward_bind":{"x":-0.8618414,"y":0.05424137,"z":0.5042689},"fov":50.25556,"position":{"x":-98.65538,"y":69.27575,"z":414.9276},"position_bind":{"x":-98.6553802490234,"y":69.275749206543,"z":414.927642822266},"target":{"x":-121.8971,"y":63.29843,"z":426.7299},"target_bind":{"x":-121.897102355957,"y":63.2984275817871,"z":426.729888916016},"type":0,"up":{"x":0.04681638,"y":0.9985278,"z":-0.02739257},"up_bind":{"x":0.04681638,"y":0.9985278,"z":-0.02739257},"viewToWorldScale":22.3261} | [7 empty] | E03 | [9 empty] | R301 |  | R301 | Q070_Penetration Management | THREE_D | (30.07; -126.47; 21.12) | (98.66; -414.93; 69.28) | (37.15; -130.07; 19.29) | (121.90; -426.73; 63.30) | Q070_Penetration Management | To do |  |  |  |  | 000001-TP01-3DM-AA1-BUA-ZZ-TB-ND-Building_A.rvt | 5232431934913322828 | Active | (37.15; -130.07; 19.29) | (121.90; -426.73; 63.30)
b8c51037-6945-48da-b6f3-aedc4bf9aa50 | 53 | Snapshot | 2026-03-16 08:04 | Solved | None | S030_Arrangement | admin rhyba-engineering.com | admin rhyba-engineering.com | Not set | admin rhyba-engineering.com |  | S030 | 04_Sanitary | true | 2026-04-09 08:14 |  | 2026-04-09 08:14 |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.1541767,"y":-0.3322726,"z":-0.9304969},"forward_bind":{"x":0.1541767,"y":-0.3322726,"z":-0.9304969},"fov":50.25556,"position":{"x":-77.36885,"y":56.27845,"z":330.0197},"position_bind":{"x":-77.3688507080078,"y":56.2784538269043,"z":330.019744873047},"target":{"x":-71.96436,"y":54.84793,"z":312.2319},"target_bind":{"x":-71.9643630981445,"y":54.8479347229004,"z":312.23193359375},"type":0,"up":{"x":0.05431469,"y":0.9431834,"z":-0.3278033},"up_bind":{"x":0.05431469,"y":0.9431834,"z":-0.3278033},"viewToWorldScale":13.94168} | [7 empty] | E02 | [9 empty] | R200 |  | R200 | S030_Arrangement | THREE_D | (23.58; -100.59; 17.15) | (77.37; -330.02; 56.28) | (21.93; -95.17; 16.72) | (71.96; -312.23; 54.85) | S030_Arrangement | Tracking |  |  |  |  | 1321_02_3DM_PP1_Q_L02_PIP_XXX.nwc | 8622159029130283572 | Active | (21.93; -95.17; 16.72) | (71.96; -312.23; 54.85)
a4b91710-445a-4660-a6fb-1285a0801330 | 54 | Snapshot | 2026-03-23 08:10 | Open | None | Q050_Skid Coordination | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-03-24 12:00 | admin rhyba-engineering.com |  | Q050 | 06_BIM/3D-Coordination | true | 2026-04-09 08:11 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.05717525,"y":-0.3531603,"z":-0.9338141},"forward_bind":{"x":0.01141843,"y":-0.9823902,"z":-0.1864913},"fov":50.25556,"position":{"x":-70.78405,"y":58.58633,"z":317.7315},"position_bind":{"x":-1084.41886822586,"y":1488.0928894043,"z":-827.486589276525},"target":{"x":-67.55917,"y":55.29542,"z":309.8796},"target_bind":{"x":-1078.53810308877,"y":1404.50370864868,"z":-841.805097357288},"type":0,"up":{"x":0.02158275,"y":0.9355628,"z":-0.3525002},"up_bind":{"x":0.001655619,"y":0.999633,"z":-0.02704039},"viewToWorldScale":9.505765} | [7 empty] | E02 |  |  |  |  | 6382139051625921776:2525722254454550804 | 35C |  |  |  | R200 |  | R200 | Q050_Skid Coordination | THREE_D | (21.57; -96.84; 17.86) | (70.78; -317.73; 58.59) | (20.59; -94.45; 16.85) | (67.56; -309.88; 55.30) | Q050_Skid Coordination | To do |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (20.59; -94.45; 16.85) | (67.56; -309.88; 55.30)
df3ecd2a-1ffa-4182-badb-b90dcc9c8a9e | 55 | Snapshot | 2026-04-07 08:11 | Open | None | P040_PID | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-04-15 12:00 | admin rhyba-engineering.com |  | P040 | 05_Process Engineering | true | 2026-04-09 08:11 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.05717525,"y":-0.3531603,"z":-0.9338141},"forward_bind":{"x":0.01141843,"y":-0.9823902,"z":-0.1864913},"fov":50.25556,"position":{"x":-70.78405,"y":58.58633,"z":317.7315},"position_bind":{"x":-1084.41886822586,"y":1488.0928894043,"z":-827.486589276525},"target":{"x":-69.54133,"y":56.51754,"z":307.387},"target_bind":{"x":-1082.15269259415,"y":1435.54561233521,"z":-846.350526510124},"type":0,"up":{"x":0.02158275,"y":0.9355628,"z":-0.3525002},"up_bind":{"x":0.001655619,"y":0.999633,"z":-0.02704039},"viewToWorldScale":9.505765} | [7 empty] | E02 |  |  |  |  | 6382139051625921776:2525722254454550804 | 35C |  |  |  | R200 |  | R200 | P040_PID | THREE_D | (21.57; -96.84; 17.86) | (70.78; -317.73; 58.59) | (21.20; -93.69; 17.23) | (69.54; -307.39; 56.52) | P040_PID | To do |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (21.20; -93.69; 17.23) | (69.54; -307.39; 56.52)
fd4c3ce4-cc8b-41f5-94ea-194816825378 | 56 | Snapshot | 2026-04-08 08:12 | Open | None | P050_Assembly | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-04-22 12:00 | admin rhyba-engineering.com |  | P050 | 05_Process Engineering | true | 2026-04-09 08:12 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":-0.6877981,"y":-0.09786,"z":-0.7192755},"forward_bind":{"x":-0.4075314,"y":-0.8076428,"z":-0.4261822},"fov":50.25556,"position":{"x":-148.8814,"y":34.44687,"z":302.0143},"position_bind":{"x":-1226.83400916368,"y":874.950566864014,"z":-856.147924747288},"target":{"x":-157.8682,"y":36.68473,"z":297.9279},"target_bind":{"x":-1243.22188455324,"y":931.792252349853,"z":-863.599761781511},"type":0,"up":{"x":-0.06763256,"y":0.9952002,"z":-0.07072779},"up_bind":{"x":-0.004878885,"y":0.9999751,"z":-0.005102169},"viewToWorldScale":5.057216} | [7 empty] | E01 |  |  |  |  | 6382139051625921776:2525722254454550804 | 35C |  |  |  | R100 |  | R100 | P050_Assembly | THREE_D | (45.38; -92.05; 10.50) | (148.88; -302.01; 34.45) | (48.12; -90.81; 11.18) | (157.87; -297.93; 36.68) | P050_Assembly | To do |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (48.12; -90.81; 11.18) | (157.87; -297.93; 36.68)
774e8b66-62a1-4ef2-b854-13ec0930a49e | 57 | Snapshot | 2026-04-09 08:12 | In progress | None | Q070_Penetration Management | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-04-14 12:00 | admin rhyba-engineering.com |  | Q070 | 06_BIM/3D-Coordination | true | 2026-04-09 08:14 | 2026-04-09 08:14 |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.3781762,"y":-0.2092212,"z":-0.9017811},"forward_bind":{"x":0.1230285,"y":-0.9480503,"z":-0.293368},"fov":50.25556,"position":{"x":-174.2241,"y":38.45641,"z":315.7447},"position_bind":{"x":-1273.04787563887,"y":976.792897033691,"z":-831.109776798557},"target":{"x":-174.3802,"y":39.85118,"z":305.5615},"target_bind":{"x":-1273.33244494729,"y":1012.22009506226,"z":-849.679378044628},"type":0,"up":{"x":0.08091331,"y":0.9778683,"z":-0.192942},"up_bind":{"x":0.005939835,"y":0.999882,"z":-0.01416384},"viewToWorldScale":4.625438} | [7 empty] | E01 |  |  |  |  | 6382139051625921776:2525722254454550804 | 35C |  |  |  | R100 |  | R100 | Q070_Penetration Management | THREE_D | (53.10; -96.24; 11.72) | (174.22; -315.74; 38.46) | (53.15; -93.14; 12.15) | (174.38; -305.56; 39.85) | Q070_Penetration Management | Tracking |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (53.15; -93.14; 12.15) | (174.38; -305.56; 39.85)
2762cc2a-9999-41b3-a74a-deb83c488e63 | 58 | Snapshot | 2026-04-09 08:13 | In progress | None | H020_Equipment | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-04-29 12:00 | admin rhyba-engineering.com |  | H020 | 03_HVAC | true | 2026-04-09 08:14 | 2026-04-09 08:14 |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.3781762,"y":-0.2092212,"z":-0.9017811},"forward_bind":{"x":0.1230285,"y":-0.9480503,"z":-0.293368},"fov":50.25556,"position":{"x":-174.2241,"y":38.45641,"z":315.7447},"position_bind":{"x":-1273.04787563887,"y":976.792897033691,"z":-831.109776798557},"target":{"x":-160.3091,"y":39.85118,"z":302.4275},"target_bind":{"x":-1247.67306942647,"y":1012.21999816895,"z":-855.394360064527},"type":0,"up":{"x":0.08091331,"y":0.9778683,"z":-0.192942},"up_bind":{"x":0.005939835,"y":0.999882,"z":-0.01416384},"viewToWorldScale":4.625438} | [7 empty] | E01 |  |  |  |  | 6382139051625921776:2525722254454550804 | 35C |  |  |  | R100 |  | R100 | H020_Equipment | THREE_D | (53.10; -96.24; 11.72) | (174.22; -315.74; 38.46) | (48.86; -92.18; 12.15) | (160.31; -302.43; 39.85) | H020_Equipment | Tracking |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (48.86; -92.18; 12.15) | (160.31; -302.43; 39.85)
d4478c86-a99f-4484-80db-d1c73a057843 | 59 | Snapshot | 2026-04-09 08:13 | Open | None | P040_PID | admin rhyba-engineering.com | admin rhyba-engineering.com | 2026-04-21 12:00 | admin rhyba-engineering.com |  | P040 | 05_Process Engineering | true | 2026-04-09 08:13 |  |  |  |  | 0 | {"exist_bind":true,"exist_target":true,"forward":{"x":0.3781762,"y":-0.2092212,"z":-0.9017811},"forward_bind":{"x":0.1230285,"y":-0.9480503,"z":-0.293368},"fov":50.25556,"position":{"x":-174.2241,"y":38.45641,"z":315.7447},"position_bind":{"x":-1273.04787563887,"y":976.792897033691,"z":-831.109776798557},"target":{"x":-168.0963,"y":37.19701,"z":303.4171},"target_bind":{"x":-1261.87343129783,"y":944.804151916504,"z":-853.589778278256},"type":0,"up":{"x":0.08091331,"y":0.9778683,"z":-0.192942},"up_bind":{"x":0.005939835,"y":0.999882,"z":-0.01416384},"viewToWorldScale":4.625438} | [7 empty] | E01 |  |  |  |  | 6382139051625921776:2525722254454550804 | 35C |  |  |  | R100 |  | R100 | P040_PID | THREE_D | (53.10; -96.24; 11.72) | (174.22; -315.74; 38.46) | (51.24; -92.48; 11.34) | (168.10; -303.42; 37.20) | P040_PID | To do |  |  |  |  | TRL_0003_T2500.nwd | 6382139051625921776 | Active | (51.24; -92.48; 11.34) | (168.10; -303.42; 37.20)

## Info
Revizto Export to Excel
Author | admin rhyba-engineering.com (admin@rhyba-engineering.com)
Exported | 2026-04-09 08:16
Project | Rhyba-Test (871573)