## Master Register
Document Number | Document Title | Discipline | Asset Type | Required Status | Required Date | Notes
P-PR-001 | P&ID Process Overview | Process | Piping | Approved | 2026-05-01
P-PR-002 | P&ID Reactor Area | Process | Piping | Approved | 2026-05-01
P-PR-003 | P&ID Utilities | Process | Piping | Signed | 2026-04-15
I-IN-001 | Instrument Index Rev 0 | Instrumentation | Instruments | Approved | 2026-05-15
I-IN-002 | Control Valve Datasheet | Instrumentation | Valves | Signed | 2026-04-30
I-IN-003 | Safety Valve Datasheet | Instrumentation | Valves | Approved | 2026-05-15
M-EQ-001 | Equipment List Rev 0 | Mechanical | Equipment | Approved | 2026-05-01
M-EQ-002 | Pump Datasheet P-101 | Mechanical | Equipment | Signed | 2026-04-20
M-EQ-003 | Heat Exchanger Datasheet E-201 | Mechanical | Equipment | In Review | 2026-06-01
M-EQ-004 | Material Certificate Vessel V-301 | Mechanical | Equipment | Approved | 2026-05-30
M-PI-001 | Pipe Spec A1 (CS 150#) | Piping | Piping | Approved | 2026-04-15
M-PI-002 | Pipe Spec B1 (SS 300#) | Piping | Piping | Signed | 2026-04-15
M-PI-003 | Valve Part List | Piping | Valves | In Review | 2026-05-15
C-CI-001 | Civil Foundation Drawing | Civil | Civil | Approved | 2026-06-01
E-EL-001 | Electrical SLD Rev 0 | Electrical | Electrical | In Review | 2026-06-15
E-EL-002 | Cable Schedule Rev 0 | Electrical | Electrical | Approved | 2026-06-15
Q-BIM-001 | BIM Coordination Report 1 | BIM | BIM | Signed | 2026-04-30
Q-BIM-002 | Clash Resolution Log | BIM | BIM | In Review | 2026-05-15