## Navisworks Export
Document Number | Description | Discipline | Model File | Object Type | Status | Revision | Date Modified | Clash Count | Approved By | Comments
M-EQ-001 | Equipment List Rev 0 | Mechanical | Process_Equipment.nwd | Equipment | Approved | B | 2026-03-18 | 0 | T.Weber | OK
M-EQ-002 | Pump Datasheet P-101 | Mechanical | Process_Equipment.nwd | Pump | Signed | A | 2026-03-22 | 0 | T.Weber | Certified
M-EQ-003 | Heat Exchanger Datasheet E-201 | Mechanical | Process_Equipment.nwd | HEX | In Review | A | 2026-04-05 | 3 |  | Pending vendor docs
M-EQ-004 | Material Certificate Vessel V-301 | Mechanical | Vessels.nwd | Vessel | Approved | A | 2026-03-30 | 0 | T.Weber | MTR attached
M-PI-003 | Valve Part List | Piping | Piping_Model.nwd | Valve | In Review | A | 2026-04-10 | 2 |  | Awaiting approval
C-CI-001 | Civil Foundation Drawing | Civil | Civil_Structure.nwd | Foundation | Approved | A | 2026-03-15 | 0 | T.Weber
Q-BIM-001 | BIM Coordination Report 1 | BIM | Coordination.nwd | Clash Report | Signed | A | 2026-04-01 | 0 | T.Weber | Round 1 complete
Q-BIM-002 | Clash Resolution Log | BIM | Coordination.nwd | Clash Log | In Review | B | 2026-04-10 | 12 |  | Active clashes
E-EL-001 | Electrical SLD Rev 0 | Electrical | Electrical.nwd | SLD | In Review | A | 2026-04-08 | 0 |  | Under review