## SharePoint
Name | Title | Discipline | Approval Status | Version | Modified | Modified By | File Size (KB) | Content Type | Path
P-PR-001_Rev-B.pdf | P&ID Process Overview | Process | Approved | 2.0 | 2026-03-15 | T. Weber | 245 | Document | Documents/Process/
P-PR-002_Rev-A.pdf | P&ID Reactor Area | Process | Draft | 1.0 | 2026-04-01 | M. Salihi | 312 | Document | Documents/Process/
I-IN-001_Rev-A.pdf | Instrument Index Rev 0 | Instrumentation | Approved | 1.0 | 2026-03-20 | M. Salihi | 156 | Document | Documents/Instrumentation/
I-IN-002_Rev-A.pdf | Control Valve Datasheet | Instrumentation | Approved | 1.0 | 2026-03-25 | D. Butumovic | 89 | Document | Documents/Instrumentation/
M-EQ-001_Rev-B.pdf | Equipment List Rev 0 | Mechanical | Approved | 2.0 | 2026-03-18 | T. Weber | 423 | Document | Documents/Mechanical/
M-EQ-002_Rev-A.pdf | Pump Datasheet P-101 | Mechanical | Signed | 1.0 | 2026-03-22 | T. Weber | 201 | Document | Documents/Mechanical/
M-PI-001_Rev-D.pdf | Pipe Spec A1 (CS 150#) | Piping | Approved | 4.0 | 2026-02-28 | D. Butumovic | 167 | Document | Documents/Piping/
E-EL-001_Rev-A.pdf | Electrical SLD Rev 0 | Electrical | Under Review | 1.0 | 2026-04-08 | M. Salihi | 334 | Document | Documents/Electrical/
Q-BIM-001_Rev-A.pdf | BIM Coordination Report 1 | BIM | Signed | 1.0 | 2026-04-01 | T. Weber | 512 | Document | Documents/BIM/
Q-BIM-002_Rev-B.pdf | Clash Resolution Log | BIM | Under Review | 2.0 | 2026-04-10 | M. Salihi | 78 | Document | Documents/BIM/
E-EL-002_Rev-A.pdf | Cable Schedule Rev 0 | Electrical | Approved | 1.0 | 2026-04-02 | D. Butumovic | 290 | Document | Documents/Electrical/
P-PR-003_Rev-C.pdf | P&ID Utilities | Process | Signed | 3.0 | 2026-03-10 | D. Butumovic | 198 | Document | Documents/Process/